## Action Plan
Group |  | Project Name
Project Summary
ACTION PLAN
ACTION | RESPONSIBLE | PRIORITY | STATUS | START DATE | END DATE | NOTES
GOAL #1 Create database
Create ERD to describe relationships between tables | RB | High | Complete | 2025-11-22 | 2025-12-04
Generate data for input into database tables + document process | BG | High | Complete | 2025-11-22 | 2025-12-04
Create database in MySQL + document process | BG | High | Complete | 2025-11-22 | 2025-12-04
Fix bugs in data generation process | RB | High | Complete | 2025-12-05 | 2025-12-08
GOAL #2 Create SQL queries
Queries 1–4 + 7–9 + documentation | RB | High | Complete | 2025-11-24 | 2025-12-10
Queries 14–19 + documentation | BG | High | Complete | 2025-11-24 | 2025-12-10
Queries 10–13 + documentation | AUO | High | Complete | 2025-11-24 | 2025-12-10
Queries 5–6 + documentation | MT | High | Complete | 2025-11-24 | 2025-12-10
GOAL #3 Polish documentation
Create github pages website | RB | Medium | Complete | 2025-11-24 | 2025-12-11
Make main README.md file | All group members | High | Complete | 2025-11-24 | 2025-12-11
Make README.md file for data_generation subdirectory | All group members | High | Complete | 2025-11-24 | 2025-12-11
Make README.md file for sql_queries subdirectory | All group members | High | Complete | 2025-11-24 | 2025-12-11

## Settings
PRIORITY OPTIONS | PROGRESS OPTIONS
High | Complete
Medium | On Hold
Low | In Progress
Not Started